## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | Use Case Name | User Story Name | Candidate Name | Scrum Team Assigned | Complexity | Risk/ Impact | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | US.101 | manage profile | view profile details | Shaurya Shukla | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 3 days
2 | 2 | Standard document | High | US.102 | manage profile | update profile details | Rajat Rastogi | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 3 days
3 | 3 | Standard document | High | US.103 | view order history | list all orders | Anjali Sharma | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 3 days
4 | 4 | Standard document | High | US.104 | view order history | view order details | Shreyanka Agarwal | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 3 days
5 | 5 | Standard document | High | US.105 | place order | add books to shopping cart | Navpreet Singh | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 3 days
6 | 6 | Standard document | High | US.106 | place order | update shopping cart | Gunjika | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 3 days
7 | 7 | Standard document | High | US.107 | place order | update shipping information and payment method | Siddhant Bansal | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional
8 | 8 | Standard document | High | US.108 | place order | submit order | Kartaveu Garg | Ganesh Prabu | Average | Low | RD:Business Requirement Doc | Non-Functional
9 | 9
10 | 10
11 | 11
12 | 12
13 | 13
14 | 14
Sprint 2 | Sprint 2
15 | 15 | Standard document | High | US:201
| 16 | Standard document | High | US:202
| 17 | Standard document | High | US:203
16 | 18 | Standard document | High | US:204
17 | 19 | Standard document | High | US:205
18 | 20
19 | 21
20 | 22
21 | 23
22 | 24
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49

## Sprint Backlog 01
| User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USBookCSMT:001 | 1 | Class Design | Gunjika | 13/7/2020 | 4 hr | 2 hrs | Completed | 1 hr
|  | 2 | Interface Design | Gunjika | 13/7/2020 | 4 hr | 2 hrs | Completed | 1 hr
2 | USBookCSMT:002 | 1 | Test plan | Gunjika | 14/7/2020 | 2 hr | 1 hr | Completed | 1 hr
3 | USBookCSMT:003 | 1 | Creating a Spring boot starter Project | Gunjika | 2020-07-14 | 2 hr | 1 hr | Completed
4 | USBookCSMT:004 | 1 | Entity Class Design | Gunjika | 2020-07-14 | 4 hr |  | in process
Note on A2: ====== ID#AAAAGgjMX2Y (2020-05-13 08:35:50) This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B2: ====== ID#AAAAGgjMX2Q (2020-05-13 08:35:50) This column is used to document the Use Case Identifier.
Note on D2: ====== ID#AAAAGgjMX3A (2020-05-13 08:35:50) Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E2: ====== ID#AAAAGgjMX2A (2020-05-13 08:35:50) List the Scrum team members assigned to this task.
Note on F2: ====== ID#AAAAGgjMX1E (2020-05-13 08:35:50) Column is used to document the date the task was assigned
Note on G2: ====== ID#AAAAGgjMX1Y (2020-05-13 08:35:50) Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H2: ====== ID#AAAAGgjMX1o (2020-05-13 08:35:50) Adjusted estimate after the Sprint has begun
Note on I2: ====== ID#AAAAGgjMX3E Task status (2020-05-13 08:35:50) Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J2: ====== ID#AAAAGgjMX2E (2020-05-13 08:35:50) Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K2: ====== ID#AAAAGgjMX2g (2020-05-13 08:35:50) Use this column to provide supporting information such as changes to the original requirement.
Note on M2: ====== ID#AAAAGgjMX1k (2020-05-13 08:35:50) This column is used to link the requirements to any resulting modules (software).
Note on N2: ====== ID#AAAAGgjMX1M (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on O2: ====== ID#AAAAGgjMX2k (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on P2: ====== ID#AAAAGgjMX0Y (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.

## Sprint Backlog 02
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
Note on A3: ====== ID#AAAAGgjMX2U (2020-05-13 08:35:50) This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: ====== ID#AAAAGgjMX1c (2020-05-13 08:35:50) This column is used to document the Use Case Identifier.
Note on D3: ====== ID#AAAAGgjMX14 (2020-05-13 08:35:50) Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: ====== ID#AAAAGgjMX20 (2020-05-13 08:35:50) List the Scrum team members assigned to this task.
Note on F3: ====== ID#AAAAGgjMX0g (2020-05-13 08:35:50) Column is used to document the date the task was assigned
Note on G3: ====== ID#AAAAGgjMX28 (2020-05-13 08:35:50) Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: ====== ID#AAAAGgjMX2w (2020-05-13 08:35:50) Adjusted estimate after the Sprint has begun
Note on I3: ====== ID#AAAAGgjMX1g Task status (2020-05-13 08:35:50) Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: ====== ID#AAAAGgjMX0k (2020-05-13 08:35:50) Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: ====== ID#AAAAGgjMX2o (2020-05-13 08:35:50) Use this column to provide supporting information such as changes to the original requirement.
Note on M3: ====== ID#AAAAGgjMX24 (2020-05-13 08:35:50) This column is used to link the requirements to any resulting modules (software).
Note on N3: ====== ID#AAAAGgjMX0M (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on O3: ====== ID#AAAAGgjMX04 (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on P3: ====== ID#AAAAGgjMX00 (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.